Time	Proposed Activities
Week starting Monday, September 14, 2015 to week starting Monday, October 26, 2015.	Prepare the project proposal – both draft and final. / Learn to use LaTeX. / Do a dummy implementation.
Week starting Monday, November 2, 2015 to week starting Monday, December 14, 2015.	Come up with a detailed literature review. / Get a deeper understanding of the Android Open Source Project (AOSP)’s implementation of the Access Point Application Programming Interface (API).
Week starting Monday, December 21, 2015 to week starting Monday, January 11, 2016.	Come up with designs for the application’s User Interface (UI). / Create dummy UIs to get a feel of how the application’s UI will work.
Week starting Monday, January 18, 2016 to week starting Monday, February 15, 2016.	Do a complete implementation of the project in Android. / Perform unit and system tests on the implementation. / Attempt to run the application on as many devices as possible.